## Sprint Backlog
Task Name | Estimate time (hour) | Take by | Status | Date Doing | Note
Finalize project scope and requirements | 2 | Nguyễn Mạnh Đăng | Done
Finalize domain glossary and business rules | 1 | Lê Thành Hòa | Done
Define user roles and permissions | 1 | Nghiêm Đặng Linh Chi | Done
Define system modules and architecture | 2 | Nguyễn Huỳnh Anh Trung | Pending
Initialize backend project and REST API structure | 2 | Nguyễn Mạnh Đăng | Pending
Design database structure | 2 | Lê Thành Hòa | Pending
Configure development Git workflow | 2 | Lê Thành Hòa | Pending
Define TestCafe testing structure | 2 | Nguyễn Huỳnh Anh Trung | Pending
Total | 14 |  | Done task: | 28.57%

## Dashboard
PROJECT PROGRESS DASHBOARD
Data automatically updates from the "Sprint Backlog" sheet (based on Status, Take by, Estimate time columns).
TOTAL TASKS |  | TASKS COMPLETED |  | TOTAL HOURS |  | COMPLETED WORK VOLUME |  | % COMPLETED
8 |  | 3 |  | 14 |  | 4 |  | 28.57%
tasks in sprint |  | 37.5% of total tasks |  | hours (Estimate time) |  | estimated hours of Done tasks |  | calculated in hours
Overall Progress: 28.6% ███████████░░░░░░░░░░░░░░░░░░░░░░░░░░░░░
1. Progress by Member
Member | Number of Tasks | Done | Doing | Pending | Fail | Total Volume (hours) | Completed (hours) | % Completion | Progress
Nguyễn Mạnh Đăng | 2 | 1 | 0 | 1 | 0 | 4 | 2 | 50% | ██████████░░░░░░░░░░
Lê Thành Hòa | 3 | 1 | 0 | 2 | 0 | 5 | 1 | 20% | ████░░░░░░░░░░░░░░░░
Nghiêm Đặng Linh Chi | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 100% | ████████████████████
Nguyễn Huỳnh Anh Trung | 2 | 0 | 0 | 2 | 0 | 4 | 0 | 0% | ░░░░░░░░░░░░░░░░░░░░
Total | 8 | 3 | 0 | 5 | 0 | 14 | 4 | 28.57% | ██████░░░░░░░░░░░░░░
Note: Names in the "Member" column must exactly match the "Take by" column in Sprint Backlog. To add a member: insert a row in the middle of the table and drag down formulas.
2. Distribution by Status
Status | Number of Tasks | % of Tasks | Total Hours | % Hours |  | How to read: • Completed work volume = total estimated hours of tasks with Status = Done (not actual hours worked). • Valid statuses: Done, Doing, Pending, Fail (select from dropdown). • Tasks without a Status are categorized as "Not Updated".
Done | 3 | 37.5% | 4 | 28.57%
Doing | 0 | 0% | 0 | 0%
Pending | 5 | 62.5% | 10 | 71.43%
Fail | 0 | 0% | 0 | 0%
Not Updated | 0 | 0% | 0 | 0%
Total | 8 | 100% | 14 | 100%
3. Charts